## Risk Log
Risk Log
Risk # | Created On | Office | Status | Description | Impact Statement | Mitigation Plan | Mitigation Plan Status | Probability (Likelihood) | Impact Rating | Severity | Target Resolution Date | Owner
1 (SAMPLE) | 2021-07-22 | ICAM PMO | Open | Duplicative ICAM offerings at agency | Different departments developed their own ICAM processes, leading to siloed ICAM services with no central control. | Develop ICAM road map, detailing current siloed state and target centralized state, and conduct activities to standardize processes and close silos, consolidating ICAM service offerings into centralized website. | 7/23/21: *Publicize standardized ICAM processes and stop duplication efforts *Coordinate content collection and plan central ICAM website *Meet with each ICAM team to gather requirements and understand content they want to include in ICAM website *Create ICAM website, offering one-stop shop for ICAM service requests |  |  |  |  | ICAM PMO